## Risk Register
Infoxchange AI Risk Register
Companion to the AI Adoption Guidelines v1.3 ¦ Last Updated: February 2026 ¦ Review: Quarterly by AI Working Group
Risk ID | AI System | Risk Category | Risk Description | Who Bears Risk | Likelihood | Consequence | Risk Rating | Existing Controls | Control Effectiveness | Residual Risk | Risk Owner | Review Date | Status | Notes
R001 | Microsoft 365 Copilot | Privacy | Staff inadvertently share sensitive client information in Copilot prompts | Clients, Organisation | Possible | Moderate | Medium | MS365 enterprise protections; Acceptable Use Policy; Staff training on data handling | Adequate | Low | IT | 2025-04-01 | Active | Standard enterprise controls in place

## Risk Categories
AI Risk Categories for Social Sector
Category | Description | Example Risks
Accuracy | AI outputs are incorrect, hallucinated, or misleading | Incorrect service information; Factual errors in reports; Hallucinated responses; Wrong calculations
Fairness | AI treats groups unfairly or produces discriminatory outcomes | Bias against non-English speakers; Inaccessible to people with disability; Discrimination in recommendations
Privacy | Personal or sensitive data is exposed, misused, or handled inappropriately | Unintended data disclosure in prompts; Training on client data; Insufficient data minimisation; Data breach
Security | AI system is exploited or compromised | Prompt injection attacks; Model extraction; Unauthorised access; Data exfiltration
Legal/Compliance | AI use violates laws, regulations, or contractual obligations | Privacy Act breach; Disability discrimination; ACNC governance failures; Contractual violations
Human Oversight | Insufficient human control over AI decisions and outputs | No override capability; Automation bias; Staff unable to intervene
Vulnerable Population | AI causes harm to people in crisis, children, or other vulnerable groups | Inappropriate crisis response; Harm to DV survivors; Child safety failures; Re-traumatisation
Operational | AI disrupts service delivery or organisational operations | System unavailability; Integration failures; Dependency on vendor; Loss of institutional knowledge
Reputational | AI failures damage trust with stakeholders or the sector | High-profile errors; Mission misalignment; Loss of funder confidence; Sector credibility damage

## Scoring Matrix
Risk Scoring Methodology
Likelihood Scale
Level | Description
Rare | May occur only in exceptional circumstances (<5% chance)
Unlikely | Could occur but not expected (5-20% chance)
Possible | Might occur at some time (20-50% chance)
Likely | Will probably occur in most circumstances (50-80% chance)
Almost Certain | Expected to occur (>80% chance)
Consequence Scale
Level | Service Impact | Financial | Reputational | Compliance
Insignificant | No noticeable impact | <$1K | No external awareness | No breach
Minor | Minor service disruption | $1K-$10K | Local awareness, quickly resolved | Minor breach, self-reported
Moderate | Partial service disruption affecting some clients | $10K-$50K | Media attention, manageable | Regulatory inquiry
Major | Significant service failure affecting vulnerable clients | $50K-$250K | Significant media, funder concern | Formal investigation
Severe | Critical harm to vulnerable people or systemic failure | >$250K | Widespread damage, sector impact | Legal action, loss of registration
Risk Rating Matrix
| Insignificant | Minor | Moderate | Major | Severe
Almost Certain | Medium | High | High | Critical | Critical
Likely | Low | Medium | High | High | Critical
Possible | Low | Medium | Medium | High | Critical
Unlikely | Low | Low | Medium | Medium | High
Rare | Low | Low | Low | Medium | Medium
Control Effectiveness Impact on Residual Risk
Effectiveness | Strong | Adequate | Partial | Weak | None
Impact | Reduces risk by 2 levels | Reduces risk by 1 level | No change | Increases risk by 1 level | Increases risk by 2 levels
Calculating Residual Risk
Step | Action
1 | Identify the inherent risk rating from the matrix above (Likelihood × Consequence)
2 | Assess how effective your existing controls are (Strong to None)
3 | Apply the effectiveness impact: Strong controls reduce rating by 2 levels; Adequate by 1 level
4 | The result is your Residual Risk - what remains after controls are applied
Example | A 'High' inherent risk with 'Adequate' controls becomes 'Medium' residual risk